## Checklist
EVENT NAME
NOT STARTED
Area | Task | Details | Responsible | Tracking | Notes
Administration | Date and Venue | Parties to agree and announcement dates and venues |  | COMPLETED
| Event Budget | Sign off Event Budget |  | STARTED
| Host Club Contacts | Host Club to confirm key persons |  | COMPLETED
| Cycling New Zealand Event Certification | Contact Cycling New Zealand for Event Certification
| Entry fees, categories, prize money and licencing requirements | Confirm and announce |  | COMPLETED
| Sponsors and benefits | CNZ to confirm national sponsors and provide local benefit packages to Host Club |  | NOT STARTED
| Online Entries | Prepare online entry portal and open and close entries |  | COMPLETED
| Post Event Survey | Prepare and send to riders, results included in event report |  | NOT STARTED
| Post Event Report | All reports to be sent to key stakeholders |  | NOT STARTED
| Post Event Budget | Finalise result and incldue in in event report |  | NOT STARTED
| Appoint and organise travel and accommodation for Commissaires | Confirm details to Commissaires |  | COMPLETED | Accommodation booked at Copthorne.
| Medals | Order and receive |  | COMPLETED
| Medal Presenters | Invite and Confirm key people |  | NOT STARTED
| Venue/s | Ensure venue has been secured and any contracts are in place |  | COMPLETED
| Community Communication | Prepare and implement plan to ensure local community are aware of the event and highlight any impact |  | COMPLETED | Club will carry this out. $120 for printing and $126.50 for 2x letterdrops.
| Event Team Uniform | Confirm what officials will be wearing and ensure they are identifiable |  | COMPLETED
| DFSNZ | Confirm attendance and prepare facilities if required |  | COMPLETED
| Race Numbers | Order and receive |  | STARTED
Operations/Course | Barrier Fencing | Design fencing plan and order sufficent fencing |  | COMPLETED | 200m from Endless fencing. $1000 in total. Shanelle to bring down on trailer
| Bike Mechanic | Arrange a local bike mechanic/store to be onsite |  | COMPLETED | Happy Valley Cycles
| Chairs and Tables | Arrange as required |  | COMPLETED
| Course Directional Signage | Arrange as required |  | COMPLETED | Need to supply a 1km to go and 5km to go. Have requested quote from Quality signs 30/3/18
| Course maps | Maps to be drawn and available for online |  | COMPLETED
| Event Announcer | Contract and brief Event Announcer |  | COMPLETED | Del flights booked
| Event courses | Confirm with Chief Cmmissaires |  | COMPLETED
| Event Schedule/Programme | Prepare event schedule including racing, registration, meetings and prizegivings |  | COMPLETED | Schedule is completed for Road Races on Saturday and Sunday. Mark to do the schedule for TT once entries are confirmed
| Event Signage | Arrange including Event Parking, Toilets, Registration, Start line, No smoking etc. |  | NOT STARTED
| Event Timing | Contract and brief Event Timing Provider |  | COMPLETED | Gavin from Timeit booked
| Event Village | Confirm layout of Event Village, ensuring all requirements are included. |  | COMPLETED | Parking in school for club members. Carpark near school used for Commissaires and then carpark beside event centre will be used for race vehicles. Village will be located in front of events centre with big screen across the road.
| Feed Zones | Confirm placement and arrange set up |  | COMPLETED | Mark has said that no events need bottle zone. Water will be carried in the commissaires cars
| Finish Gantry | Arrange Finish Gantry and Signage |  | COMPLETED | SB Events to supply finish gantry. Panels to be made up by CNZ from Expanda sign
| First Aid | Confirm First Aid Provision and Base |  | COMPLETED | Promed booked
| Food and Refreshments | Ensure sufficient available for riders, staff and spectators |  | COMPLETED | Kiwi Coffe & Kai @ Event Village. Good Vibes Coffee at Start/Finish Line
| Portoloos and Showers | Arrange as required |  | COMPLETED | Portoloos booked for start/finish line. Toilets at Events Centre available to use.
| Power | Arrange as required |  | COMPLETED | AVP bringing spare generator for finish line
| Presentations Area | Arrange including stage, backdrop, 3 Podium steps, flowers, champagne, or sponsors gifts |  | STARTED | Backs sent to AVP. Need to pack medals, jerseys and podium
| Security | Arrange as required |  | COMPLETED | First security booked - awaiting on contact details
| Sound Provider | Confirm and brief Sound System Operator |  | COMPLETED | AVP
| Start and finish areas | Arrange equipment as required (including fencing, barriers and start ramp for TT) |  | STARTED | 200m of fencing will be supplied from endless fencing. TT ramp from Jorge. Finish gantry from SB Events. Need cones for vehicle lane. Shanelle to draw up and get Mark to approve. Not using TT ramp
| Sunscreen | Arrange a free source if available |  | COMPLETED | SB Events to bring some
| Tents | Arrange for Timing, Sound and Race Base (if applicable) |  | COMPLETED
| Two Way Radios | Arrange as required |  | COMPLETED | Being supplied by Teletronics. Base station for each vehcile and then handhelds TBC. Commissaires will bring all UHF which will be used within Commissiares team and vehicles
| Vehicles | Confirm vehicles, drivers and arrange signage |  | COMPLETED | 20 vehicles required - need to work out where from. 5 motorbikes will also be at the event. 2 for lead and the remaining to assist with big races. 5 being supplied from CNZ and 1 broom from SB. Rest from club
| Volunteers | Confirm requirements, Recruit, Train and brief Volunteers |  | STARTED | Plan in place. Need to do sheets for each volunteer of where they will stand and then breifing notes
| Waste Management | Arrange as required |  | STARTED | CDC Sourcing bins
| Water Source | Arrange a free source if available |  | NOT STARTED
Marketing | Event Website | Update with event details |  | STARTED
| Marketing | Agree on local and national marketing material |  | STARTED
| Social Media | Confirm social media plan |  | STARTED
| Signage Plan | Confirm plan for sponsors signage and placement |  | NOT STARTED
| Local Sponsorship | Secure local sponsors. |  | NOT STARTED
| Attending Media | Confirm and manage attending media |  | NOT STARTED
| Media Spokespersons | Confirm and communication authorised media spokespersons |  | NOT STARTED
| Event Photographer | Contact and brief photographer for all events. |  | COMPLETED | Dave Lintott
| Event Poster | Prepare, print and distribute event poster |  | COMPLETED
Compliance | Health and Safety Manual | Complete Safety Management Plan including Risk Register |  | COMPLETED | Need to put event onto Blerter as well.
| Event Manual | Prepare and send to riders |  | STARTED
| Insurance | Confirm insurance cover |  | COMPLETED
| Emergency Services | Ensure all local emergencies and medical services are aware of event |  | COMPLETED
| Traffic Management | Prepare, submit and receive approved Traffic Management plans |  | COMPLETED | ACM providing traffic management which will be managed by Andrew from Higgins. All road closures approved. TMP received
| External Vendors | Ensure all temporary vendors have permits to operate |  | NOT STARTED
| Council Approvals | Ensure any council requirements are adhered to |  | COMPLETED | All Road Closures have been approved with Council.